## Functional Requirements
ID | Requirement | Funcationality Order | PoC | MVP | Type | Hours | Expected Date | Comments
1 | One Stop Shop - All resources must be bookable and managed via one tool regardless of resource required |  |  | Y | Global | 40 |  | Table creation, views and Forms configurations
2 | Use ‘Smart Working’ Branding |  | Y | Y | Global | 0.5
3 | Name of application: ‘ApTrefnu / MyBookings’ |  | Y | Y | Global | 0
4 | Ability to book resource independently or in any combination, and send notifications as appropriate |  |  | Y | Global | 0
5 | Ability to amend or cancel each element of a booking separately or as a whole, and send notifications as appropriate |  |  | Y | Global | 0
6 | Ability to book, amend or cancel resources across multiple sites, in any combination, and send notifications as appropriate |  |  | Y | Global | 0
7 | Ability to differentiate between ‘managed’ and ‘unmanaged’ rooms. |  |  | Y | Global | 0
8 | Ability to add, amend, suspend, or cancel facilities within resource |  |  | Y | Global | 32
9 | Ability to add, amend, suspend, or cancel the layout capability within a room, and its consequent capacity |  |  | Y | Global |  |  | Need more clarity
10 | Ability to administer the MyBookings through differing roles and access permissions of the base data. |  |  | Y | Global | 40 |  | Security roles configuration in Dataverse, the estimate include testing
11 | Ability to generate management information |  |  |  | Global |  |  | Need more clarity
12 | Ability to amend business rules to govern aspects of the system. |  |  |  | Global |  |  | Need more clarity
13 | Able to book parking / catering / inform Reception of visitors |  | part |  | Global | 40 |  | Need more clarity, This needed a form to create a form to add the visitor details and then associate the visitor with the booking
20 | Ability to access a filter mechanism to search for available resources to meet the needs of the User |  | part | Y | Landing Page | 0
21 | Ability to inform Reception of the arrival of External Visitors |  |  | Y | Landing Page | 8 |  | Sending email to reception after the host / booker by clicking on a button instantly
22 | Ability to book Hospitality |  |  |  | Landing Page | 8
23 | Ability to view all current bookings made by the User |  |  | Y | Landing Page | 4
24 | Ability to view all bookings for all Sites |  |  | Y | Landing Page | 4
30 | Ability to select one or more sites (all sites) – default to Site of user location - mandatory |  | part | Y | Filter & Search Mechanism - Check Availability of Resources |  |  | Need more clarity on what is the current site of the user?
31 | Ability to select Resource Type (Room, Car Park Space) – default to Resource Type ‘Room’ - mandatory |  |  | Y | Filter & Search Mechanism - Check Availability of Resources |  |  | Need more clarity on what is the current site of the user?
32 | Ability to enter a start date, in the format YYYY, Month, DD – default to today’s date - mandatory |  | Y | Y | Filter & Search Mechanism - Check Availability of Resources |  |  | Need more clarity on what is the current site of the user?
33 | Ability to enter a finish date, in the format YYYY, Month, DD – default to today’s date - mandatory |  |  | Y | Filter & Search Mechanism - Check Availability of Resources |  |  | Need more clarity on what is the current site of the user?
34 | Ability to enter a start time (24hr clock) – default time 00:00 - optional |  | Y | Y | Filter & Search Mechanism - Check Availability of Resources | 1
35 | Ability to enter a finish time (24hr clock) – default time 23:59 - optional |  | Y | Y | Filter & Search Mechanism - Check Availability of Resources | 0
36 | If Room selected ability to select Corporate Rooms or Departmental Rooms or Both |  |  | Y | Filter & Search Mechanism - Check Availability of Resources | 2
37 | If Room selected present list of all rooms for sites – ability to select one - optional |  |  | Y | Filter & Search Mechanism - Check Availability of Resources |  |  | Need more clarity, do you mean the screen should list out all the remaining rooms if any one of the room booked in selected / all the sites?
38 | If Room selected on an individual basis ability to view photographs of room and potential layouts |  |  |  | Filter & Search Mechanism - Check Availability of Resources | 24
39 | If Room selected – Number of Attendees – default ‘2’ - optional |  | Y | Y | Filter & Search Mechanism - Check Availability of Resources | 0.5
40 | If Room selected – Facilities required – default none - optional |  | Y | Y | Filter & Search Mechanism - Check Availability of Resources | 0
41 | If Room selected – Layout change required: yes / No – default no – optional |  |  | Y | Filter & Search Mechanism - Check Availability of Resources | 0
42 | If Car Park Space selected – Facility required (Standard, Accessibility, EVCP, All) – based on site availability - optional |  | Y | Y | Filter & Search Mechanism - Check Availability of Resources | 4
43 | Ability to find resource bookings (Room or Car Park) by selecting a Booker |  |  |  | Filter & Search Mechanism - Check Availability of Resources | 8
44 | Ability to find resource bookings (Room or Car Park) bookings by selecting a Host |  |  |  | Filter & Search Mechanism - Check Availability of Resources | 0
45 | Ability to find room Bookings by date, by invitee (internal or external), by organisation, by room identifier. |  |  |  | Filter & Search Mechanism - Check Availability of Resources | 8
46 | Ability to find Car Park Bookings by date, by vehicle registration, by visitor name (internal or external), by organisation, by parking space number. |  |  |  | Filter & Search Mechanism - Check Availability of Resources | 4
49 | Ability to select on the search results are to be presented: Calendar View OR Availability View |  |  | Y | Filter & Search Mechanism - Check Availability of Resources | 20
50 | Ability to enter the details of one or more external visitors for one or more days, including: |  |  |  | Inform Reception of External Visitor(s) | 16
| Dates expected, times of expected arrival, pre-populate booker contact details, secondary contact details, Bi-lingual requirements, indicate VIP or Diplomatic Status |  |  |  | Inform Reception of External Visitor(s) | 0
51 | Ability for Reception staff at the Site to see a list of the expected External Visitor(s), for the day in ascending time order |  |  |  | Inform Reception of External Visitor(s) | 6
55 | Ability to view all my bookings in one place as a Booker |  | Y |  | View My Current Bookings | 8
56 | Ability to view all my bookings in one place as a Host |  |  |  | View My Current Bookings | 1
57 | Ability to select my bookings by searching for an invitee |  |  |  | View My Current Bookings | 1
58 | Ability to amend or cancel bookings – either all resources booked for event or singularly |  |  |  | View My Current Bookings | 8
60 | Ability to present search results showing all bookings to date and the slots available in a manner similar to Microsoft Calendar, as blocks of time over a day. |  |  | Y | Search Results: Calendar View | 24
61 | Depending on Resource Type selected: Ability to see the Room Name, Title of the Event, Booker’s Name |  |  | Y | Search Results: Calendar View | 8
62 | Ability to click on the Booking to see the Booker’s contact details (telephone / mobile numbers, email & Instant Message) |  |  | Y | Search Results: Calendar View | 4
63 | Ability to overlay the same day across two or more sites to determine joint availability |  |  |  | Search Results: Calendar View |  |  | Need more clarity, what do you mean by overlay
64 | Ability to show the resource as ‘unavailable’ if a resource is temporarily suspended |  |  | Y | Search Results: Calendar View | 2
65 | If a resource is temporarily suspended, the ability when searching for a named resource to display a message to indicate that the room is out of service from the suspension start date until further notice (or finish date if known). |  |  | Y | Search Results: Calendar View | 1
66 | IF Resource Type ‘Rooms’ selected THEN present rooms based on the closest match in ascending order based on capacity of the room |  | Y | Y | Search Results: Availability View | 4
67 | IF Resource Type ‘Car Parking’ selected THEN, based on facility selected, present available car parking spaces |  | Y | Y | Search Results: Availability View | 4
68 | If a car parking resource is temporarily suspended do not to display the resource. |  | Y | Y | Search Results: Availability View | 0
69 | If a resource is temporarily suspended, the ability when searching for a named resource to display a message to indicate that the room is out of service from the suspension start date until further notice (or finish date if known). |  |  | Y | Search Results: Availability View | 1
70 | Ability to book meeting rooms at multiple sites for the same meeting. |  |  |  | Book a Resource (Room) | 24
71 | Ability to confirm site, date and time, number of attendees |  |  | Y | Book a Resource (Room) | 0.5
72 | Ability to auto fill the name and department of the user making the booking. |  | Y | Y | Book a Resource (Room) | 0.5
73 | Ability to view meeting room layouts /photographs / configurations / equipment available etc. to show what is available. |  |  |  | Book a Resource (Room) | 20 |  | We may not be able to render the photos
74 | Ability to select one or a combination of facilities available within the room |  |  | Y | Book a Resource (Room) | 8
75 | Notify IT/AC if technology needs to be booked |  |  |  | Book a Resource (Room) |  |  | Need more clarity
76 | Ability to request a reconfiguration of the furniture. |  |  | Y | Book a Resource (Room) | 0.5 |  | Assuming that it is the change in layout of the room
77 | When a Furniture Layout Reconfiguration is requested: |  |  | Y | Book a Resource (Room) | 40 |  | Most complex piece to implement the business logic and also need to change the list of items to be shown in the gallery of rooms.
| · Automatically add set up and clear down time to the booking for porters - 30 minutes before and after the start and end time of the meeting – total 1 hour. (see business rules); |  |  |  | Book a Resource (Room) | 0
| · Add this time to the Start and Finish times of the event as already entered; |  |  |  | Book a Resource (Room) | 0
| · Alert the user if this causes a timing clash with a prior or subsequent meeting already booked. |  |  |  | Book a Resource (Room) | 0
78 | Ability to book multiple configurations of a single room booking with times for each layout. |  |  |  | Book a Resource (Room) | 24
79 | Ability to display a notification to the user if requesting a change to room layout with less than one working day’s notice – to speak to the Porters directly |  |  | Y | Book a Resource (Room) | 0
80 | Ability to book component rooms when a ‘Suited’ room is booked |  |  | Y | Book a Resource (Room) | 4 |  | Need more clarity
81 | Ability to alert the user if the number of meeting invitees exceeds the meeting room capacity based on layout selected (see business rule). |  | part | Y | Book a Resource (Room) | 2
82 | Ability to add links to documents in iShare |  |  |  | Book a Resource (Room) |  |  | Need more clarity
83 | Ability to add a Note to the booking |  |  | Y | Book a Resource (Room) | 0
84 | On confirming Booking validate that number of invitees is equal to or less than the maximum capacity for the layout requested. |  |  | Y | Book a Resource (Room) | 0
85 | On confirming Booking validate that booking has not already been made for the date and time |  | Y | Y | Book a Resource (Room) | 2
86 | Ability for Porterage staff to see a list of Room layouts required by date and time ascending order |  |  | Y | Book a Resource (Room) | 6
90 | Ability to request to use room from the Departmental Room Owner |  |  | Y | Managed Rooms (Departmental Rooms) | 0 |  | What about the room confirmation for the user?? Should we show as pending or confirmed? If confirmed, what should we do if the owner of the departmental room cancel the request
91 | Ability for the Departmental Room Owner to Approve, or Decline Request, sending a Notification to the Booker |  |  | Y | Managed Rooms (Departmental Rooms) | 6 |  | Dependent on Requirement 90
100 | Ability to display Parking spaces in numerical order |  | Y | Y | Make a Booking (Car Parking) | 1
101 | Ability to book multiple car parking spaces together for a single site |  |  | Y | Make a Booking (Car Parking) | 2
102 | Ability to enter parking requirements e.g. date/time/duration/ and the system will find a suitable parking space for the booker. |  | Y | Y | Make a Booking (Car Parking) | 4
103 | Ability to book Car park spaces in 15 minute incremental time slots (except Electric Vehicle spaces – see below) |  | Y | Y | Make a Booking (Car Parking) | 8 |  | is it at the time of booking or after booking?
104 | Ability to add 30 minutes to the finish time |  | Y | Y | Make a Booking (Car Parking) | 0
105 | Ability to select an option for the booker to be reminded to book planned parking if over the 4 weeks ahead. |  |  | Y | Make a Booking (Car Parking) | 12
106 | Ability to reject Car Registration format where the following has been entered by the Booker: |  | Y | Y | Make a Booking (Car Parking) | 4
| TBA / TBC / NK / N/A – that is, less than four alpha characters; |  |  |  | Make a Booking (Car Parking) | 0
| To Be Advised / To Be Added / To Be Confirmed / Not Known / Not Applicable / Not Available; |  |  |  | Make a Booking (Car Parking) | 0
| Should be a least one number |  |  |  | Make a Booking (Car Parking) | 0
107 | Ability to indicate whether the Car Parking Space is for a Visiting Officer or an External Visitor |  |  | Y | Make a Booking (Car Parking) | 0.5
108 | Ability to select whether the Car Parking Space required is a standard space, an accessibility space, an electric vehicle charging point, or electric vehicle charging point Accessibility space depending on the site selected. |  |  |  | Make a Booking (Car Parking) | 2
109 | Ability to add a Note to the booking |  |  | Y | Make a Booking (Car Parking) | 0.5
110 | On confirming Booking validate that booking has not already been made for the date and time |  | Y | Y | Make a Booking (Car Parking) | 2
111 | Ability for Security Gate staff to see list of expected Visitors, car details in date and time ascending order |  |  | Y | Make a Booking (Car Parking) | 24
111a | Ability to Notify Visiting Officers and External Visitors confirming car parking detail (subject to type of space) |  |  | Y | Make a Booking (Car Parking) | 1
112 | IF the Site has bookable Car parking spaces available THEN the following applies: |  |  |  | External Visitor Only (All Facilities – Standard, Accessibility, Electric Charging) | 16
113 | Ability to input an email address and mobile phone number of the visitor |  | part | Y | External Visitor Only (All Facilities – Standard, Accessibility, Electric Charging) | 0
114 | Ability to make the completion external visitor details mandatory |  | Y | Y | External Visitor Only (All Facilities – Standard, Accessibility, Electric Charging) | 0
115 | Ability to stop a booking and alert the user IF internal staff details are entered into external visitor detail section (based on email address) |  | Y | Y | External Visitor Only (All Facilities – Standard, Accessibility, Electric Charging) | 0
116 | Ability to book Car park spaces restricted to 4 weeks in advance of meeting date (see Electric Charging rules – see below) |  | Y | Y | External Visitor Only (All Facilities – Standard, Accessibility, Electric Charging) | 0
117 | IF the Site has bookable Car parking spaces available THEN the following applies: |  |  |  | Visiting Officer Only (All Facilities – Standard, Accessibility, Electric Charging) | 16
118 | Ability to input email address |  |  | Y | Visiting Officer Only (All Facilities – Standard, Accessibility, Electric Charging) | 0
119 | Ability to make the completion internal visitor details mandatory. |  |  | Y | Visiting Officer Only (All Facilities – Standard, Accessibility, Electric Charging) | 0
120 | Ability to stop a booking and alert the user IF External Visitor details are entered into internal visitor detail section (based on email address) |  |  | Y | Visiting Officer Only (All Facilities – Standard, Accessibility, Electric Charging) | 0
121 | Ability to book Car park spaces restricted to 1 week in advance of meeting date (see Electric Charging rules – see below) |  |  | Y | Visiting Officer Only (All Facilities – Standard, Accessibility, Electric Charging) | 0
122 | IF the Site has Electric Charging Spaces available for either Internal OR External Visitors THEN the following applies: |  |  |  | Electric Vehicle Charging Points (Internal and External Visitors) | 8
123 | Ability to book Electric Charging Car Park spaces for External Visitors restricted to a maximum of 4 weeks in advance. |  | Y | Y | Electric Vehicle Charging Points (Internal and External Visitors) | 0
124 | Ability to book Electric Charging Car Park spaces for Visiting Officers restricted to a maximum of 7 calendar days (5 working days) in advance. |  |  |  | Electric Vehicle Charging Points (Internal and External Visitors) | 0
125 | Ability to Book Electric Charging Car Park spaces 1 hour time slots. |  | Y | Y | Electric Vehicle Charging Points (Internal and External Visitors) | 0
126 | Ability to book an electric Car Parking space for a Maximum 4 hours and cannot be booked again for that day. |  | part | Y | Electric Vehicle Charging Points (Internal and External Visitors) | 0
127 | Ability to request and confirm the booker has read the Electric Vehicle Parking Policy and will comply with its requirements? |  | Y | Y | Electric Vehicle Charging Points (Internal and External Visitors) | 0
128 | Ability to request and confirm the space has been booked exclusively for an electric vehicle |  | Y | Y | Electric Vehicle Charging Points (Internal and External Visitors) | 0
129 | IF the Site has bookable Accessibility spaces THEN the following applies: |  |  |  | Accessibility Space (Internal and External Visitors) | 8
130 | Ability to request and confirm the space has been booked for a Blue Badge holder |  | Y | Y | Accessibility Space (Internal and External Visitors) | 0
131 | Ability to alert the Booker the Blue Badge holder is requi red to present their Blue Badge at the Security Gate |  |  | Y | Accessibility Space (Internal and External Visitors) | 0
132 | IF the Site has bookable Accessibility Electric Charging spaces THEN the following applies: |  |  |  | Accessibility Electric Vehicle Charging Space (Internal & External Visitors) | 24
133 | Ability to request and confirm the space has been booked for a Blue Badge holder |  | Y | Y | Accessibility Electric Vehicle Charging Space (Internal & External Visitors) | 0
134 | Ability to alert the Booker the Blue Badge holder is required to present their Blue Badge at the Security Gate |  |  | Y | Accessibility Electric Vehicle Charging Space (Internal & External Visitors) | 0
135 | Ability to book Electric Charging Car Park spaces for an External Vistitor is restricted to a maximum of 4 weeks in advance. |  | Y | Y | Accessibility Electric Vehicle Charging Space (Internal & External Visitors) | 0
136 | Ability to book Electric Charging Car Park spaces for Visiting Officers is restricted to a maximum of 7 calendar (5 working) days in advance. |  | Y | Y | Accessibility Electric Vehicle Charging Space (Internal & External Visitors) | 0
137 | Ability to book an electric Car Parking space for a Maximum 4 hours, the same registration cannot use the charging point again that day. |  | part | Y | Accessibility Electric Vehicle Charging Space (Internal & External Visitors) | 0
138 | Ability to request and confirm the booker has read the Electric Vehicle Parking Policy and will comply with its requirements? |  | Y | Y | Accessibility Electric Vehicle Charging Space (Internal & External Visitors) | 0 |  | add this in ER diagram with new field in resorce table
139 | Ability to request and confirm the space has been booked exclusively for an electric vehicle |  | Y | Y | Accessibility Electric Vehicle Charging Space (Internal & External Visitors) | 0
140 | Ability to select internal members of staff as invitees to the event |  |  |  | Selecting Invitees (Internal Staff) | 8
141 | Ability to enter the name, organisation and email address of an External invitee |  |  |  | Selecting Invitees (Internal Staff) | 0
142 | Ability to show by default the booker’s calendar |  |  |  | Selecting Invitees (Internal Staff) |  |  | need clarity, where should I show this?
143 | Ability to find internal staff availability from their outlook calendar |  |  |  | Selecting Invitees (Internal Staff) | 24
144 | Ability to view potential invitees’ calendars side-by-side |  |  |  | Selecting Invitees (Internal Staff) |  |  | need more clarity, where and how do you want this???
145 | Ability to send notification of booking details to invitees, or if internal staff insert event into their calendar on booking. |  |  |  | Selecting Invitees (Internal Staff) | 40
146 | Ability to request Refreshments |  |  |  | Booking Hospitality | 30
| IF the Site supplies Refreshments, AND an External Visitor has been invited* |  |  |  | Booking Hospitality | 0
147 | Ability to select Refreshments required by linking out to Caterer’s system, in another tab |  |  |  | Booking Hospitality | 0
148 | Ability to amend or cancel refreshments if the arrangements are amended or cancelled. |  |  |  | Booking Hospitality | 0
150 | Ability by the Booker and Host to Amend all aspects of a booking, including changing Booker and Host by the other party. |  |  | Y | Amend a Booking |  |  | Need more clarity on, including changing Booker and Host by the other party.
151 | Depending on the nature of the change, notify affected invitees or update calendar event |  |  | Y | Amend a Booking |  |  | Need more clarity, What all the events need to be invited to parties?
152 | IF Date and Time are amended THEN the all associated bookings for rooms and car parking spaces should be re-validated, raising a warning to the User that there are conflicts – and advising not to progress or cancel booking(s) |  |  | Interim | Amend a Booking | 4
| NB – interim solution for MVP – Booker has to cancel bookings and rebook |  |  |  | Amend a Booking | 0
155 | Ability to Cancel a Booking for each individual element of an event. |  |  | Y | Cancel a Booking Completely or In-Part | 8
156 | Ability to Cancel All Resources Booked for that Event from a single action. |  | Y | Y | Cancel a Booking Completely or In-Part | 0
157 | Ability to send Notifications to all Invitees, remove calendar events, inform Catering (if refreshments have been ordered) on cancellation. |  |  |  | Cancel a Booking Completely or In-Part | 0
160 | Ability to see Expected Arrivals in real time |  |  | Y | Arrival of External Visitor at Security Gate |  |  | Need more clarity, about what you mean by realtime ??
161 | Ability for the Security Guard to view External Visitor details |  |  | Y | Arrival of External Visitor at Security Gate | 2
162 | Ability to acknowledge arrival on system |  |  | Y | Arrival of External Visitor at Security Gate |  |  | who should do this?? Security / visitor??
163 | Ability to confirm or not the details of the visitor were correct as booked |  |  | Y | Arrival of External Visitor at Security Gate |  |  | Not clear on the statement ..
[5 empty] | Total Hours | 722.5
[5 empty] | Implementation in Days | 90.3125
[5 empty] | Months | 4.5156
Note on G143: With 15% buffer time with one developer! Need to add 15% if more than one developer for code integration and testing.